## OKRs-Sample
| OKR Setting Sheet | Business Line: Content Year: 2023 |  |  |  | Period Highlight: | 3
[8 empty] | 5=Achieved | [5 empty] | 4=On Track |  |  |  |  | 3=At Risk |  |  |  |  | 2=Missed By Margin (MBM) | [8 empty] | 1=Missed |  |  |  |  | 0=Deferred
[7 empty] | WEEKS IN QUARTER 1 |  |  |  |  | 6 | [7 empty] | WEEKS IN QUARTER 2 |  |  |  |  | 7 | [7 empty] | WEEKS IN QUARTER 3 |  |  |  |  | 8 | [7 empty] | WEEKS IN QUARTER 4 |  |  |  |  | 9
| OBJECTIVES AND KEY RESULTS | ASSIGNEE | DUE DATE | FINAL STATUS | TIMELINE | PERCENT ACHIEVED | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52
1 | Objective 1: Increase website content visits by 20%.
| KR 1: Launch seasonal campaigns to boost site visits by 10% from last year- New year resolution kit, Summer tips. | A | 2023-03-31 | Achieved | Q1 | 100% | WEEKS IN QUARTER 1 1: 4; WEEKS IN QUARTER 1 2: 0; WEEKS IN QUARTER 1 3: 3; WEEKS IN QUARTER 1 4: 4; WEEKS IN QUARTER 1 5: 4; 6 6: 4; 6 7: 4; 6 8: 4; 6 9: 4; 6 10: 4; 6 11: 4; 6 12: 4; 6 13: 5
| KR 2: Double the social media promotional posts and personalized mailers for contents to potential members. | B | 2023-12-31 | Missed | Q4 | 50% | WEEKS IN QUARTER 4 40: 0; WEEKS IN QUARTER 4 41: 0; WEEKS IN QUARTER 4 42: 0; WEEKS IN QUARTER 4 43: 0; WEEKS IN QUARTER 4 44: 3; 9 45: 3; 9 46: 3; 9 47: 3; 9 48: 3; 9 49: 3; 9 50: 3; 9 51: 3; 9 52: 1
| KR 3: Organize one educational forum per month basis the fresh content theme. Achieve 20% participants to visit content on site. | B | 2023-06-30 | MBM | Q2,Q3 | 90% | WEEKS IN QUARTER 2 14: 4; WEEKS IN QUARTER 2 15: 4; WEEKS IN QUARTER 2 16: 4; WEEKS IN QUARTER 2 17: 4; WEEKS IN QUARTER 2 18: 4; 7 19: 4; 7 20: 4; 7 21: 4; 7 22: 4; 7 23: 4; 7 24: 4; 7 25: 3; 7 26: 2; WEEKS IN QUARTER 3 27: 4; WEEKS IN QUARTER 3 28: 4; WEEKS IN QUARTER 3 29: 4; WEEKS IN QUARTER 3 30: 4; WEEKS IN QUARTER 3 31: 4; 8 32: 4; 8 33: 4; 8 34: 4; 8 35: 3; 8 36: 3; 8 37: 3; 8 38: 3; 8 39: 2
KR 4: None
2 | Objective 2:
| KR 1: | A
| KR 2: | C
| KR 3: | C
| KR 4: | D
3 | Objective 3:
KR 1:
KR 2:
KR 3:
KR 4:
4 | Objective 4:
KR 1:
KR 2:
KR 3:
KR 4:
5 | Objective 5:
KR 1:
KR 2:
KR 3:
KR 4: